## UCP
Paquete	Puntos de Caso de Uso - Use Case Points

Unadjusted Use Case Points:

Análisis de Actores
Complejidad	Definición	Peso	Cantidad	Peso Total
Simple	Representa otro sistema con una interfase definida de aplicación programada	1	3	3
Promedio	Interactúa con otra aplicación a través de un protocolo o interacción humana a través de terminal de línea	2	1	2
Complejo	Interacción humana a través de interfase usuario gráfica	3	4	12
TOTAL			8	17

Análisis de Casos de Uso
Complejidad	Definición	Peso	Cantidad	Peso Total
Simple	Tiene 3 o menos transacciones incluyendo cursos alternativos. Casos de uso con menos de 5 objetos de análisis	3	27	81
Promedio	Tiene 3 a 7 transacciones incluyendo cursos alternativos. Casos de uso con 5 a 10 objetos de análisis	6	5	30
Complejo	Tiene más de 7 transacciones incluyendo cursos alternativos. Casos de uso con más de 10 objetos de análisis	12	0	0
TOTAL			32	111

Total de Unadjusted Case Points				128

Adjusted Use Case Points: AUCP = UUCP × TCF × EF				147.55

Esfuerzo Estimado en horas: AUCP x 10				1475.52	Hs.

	Fases:					Costo/hora	Costo de fase
	Especificación		5%	73.78	Hs.		$150.00	$11,066.40
	Análisis		10%	147.55	Hs.		$150.00	$22,132.80
	Diseño		10%	147.55	Hs.		$200.00	$29,510.40
	Construcción		50%	737.76	Hs.		$200.00	$147,552.00
	Integración		5%	73.78	Hs.		$175.00	$12,910.80
	Pruebas		15%	221.33	Hs.		$150.00	$33,199.20
	Administración		5%	73.78	Hs.		$250.00	$18,444.00
			100%	1475.52	Hs.	TOTAL	$274,815.60

## TCF
Factor de Complejidad Técnica -Technical Complexity Factor (TCF)					Ejemplo:
Factor	Descripción	Peso	Valor Asig.	Factor Calc	Comentarios		Factor	Descripción	Peso	Valor Asig.	=	Comentarios
T1	Sistema Distribuido	2	0	0	Central system		T1	Sistema Distribuido	2	0	0	Central system
T2	Tiempo de Respuesta, objetivos de performance	1	3	3	Speed is probably limited by human input		T2	Tiempo de Respuesta, objetivos de performance	1	3	3	Speed is probably limited by human input
T3	Eficiencia de Usuario Final	1	5	5	Needs to be efficient		T3	Eficiencia de Usuario Final	1	5	5	Needs to be efficient
T4	Complejidad de procesamiento interno	1	5	5	No complex calculations		T4	Complejidad de procesamiento interno	1	1	1	No complex calculations
T5	Codigo debe ser reusable	1	5	5	Si		T5	Codigo debe ser reusable	1	0	0	No
T6	Easy to install	0.5	5	2.5	Must be very easy to install
T7	Easy to use	0.5	5	2.5	Very user-friendly
T8	Portable	2	5	10	No
T9	Easy to change	1	5	5	Low maintenance cost
T10	Concurrent	1	5	5	No
T11	Includes special security objectives	1	5	5	Normal security
T12	Provides direct access for third parties	1	5	5	WEB users have direct access
T13	Special user training facilities are required	1	1	1	Few internal users, easy to use system
Total Technical factor (Tfactor):				54
				0.87

	TCF = 0.6 + (.01 × TFactor)

	TCF = 0.6 + (.01 × 27) = 0.6 + 0.27 = 0.87

				0

## EF
Factor de Entorno -Environment Factor (EF)					Ejemplo:
Factor	Descripción	Peso	Valor Asig.	Factor Calc	Comentarios		Factor	Descripción	Peso	Valor Asig.	Factor Calc	Comentarios
E1	Familiar with the project model that is used	1.5	1	1.5	Most staff is not familiar with the model		E1	Familiar with the project model that is used	1.5	1	1.5	Most staff is not familiar with the model
E2	Application experience	0.5	1	0.5	Most staff has worked many years in this applic.		E2	Application experience	0.5	4	2	Most staff has worked many years in this applic.
E3	Object-oriented experience	1	1	1	Most staff is former COBOL-programmers		E3	Object-oriented experience	1	1	1	Most staff is former COBOL-programmers
E4	Lead analyst capability	0.5	1	0.5	A consultant from Callista is used		E4	Lead analyst capability	0.5	5	2.5	A consultant from Callista is used
E5	Motivation	1	1	1	The team is highly motivated		E5	Motivation	1	5	5	The team is highly motivated
E6	Stable requirements	2	1	2	We expect some changed		E6	Stable requirements	2	2	4	We expect some changed
E7	Part-time staff	-1	3	-3	Unfortunately several staff is half-time		E7	Part-time staff	-1	3	-3	Unfortunately several staff is half-time
E8	Difficult programming language	-1	1	-1	Visual Basic		E8	Difficult programming language	-1	1	-1	Visual Basic
Total Environment Factor (Efactor):				2.5			Total Environment Factor (Efactor):				12

EF = 1.4+(-0.03 × EFactor)				1.325			EF = 1.4+(-0.03 × EFactor)				1.04

	EF = 1.4 + (-0.03 × 12) = 1.04 - 0.285 = 0.755

## Act y CU
	NOTA: Completar con los datos del Paquete	Complejidad
	Actores	Baja	Media	Alta
1	Usuario			3
2	Administrador		1
3	Cliente			1
4	proveedor	3

	Total Actores por Complejidad	3	1	4

		Complejidad
	Caso de Uso	Baja	Media	Alta
1	Alta de Usuario		2
2	ABM de artículos por proveedores	4
3	Mail de Confirmación	3
4	Modificación de usuario	2
5	Login	4
6	Baja de Usuario	4
7	Búsqueda de Artículo		3
8	Listar Artículos	4
9	Selección Carrtio de Compra	4
10	ABM de Proveedores	2
11

	Total Casos de Uso por Complejidad	27	5	0